## Sheet1
REQUIREMENT TRACEABILITY MATRIX
Project Name: | VaagBanda — Smart Mobile Expense-Splitting Application |  |  |  | VaagBanda Mobile Application
Created By: | Team CyberSquadNp |  |  |  | CyberSquadNp · Dongshin University
Date: | 2026-06-01 |  |  |  | Supervisor: Prof. Ibrahim Musa
Req ID | Requirement Description | SRS Ref | Design | Scenario | Implementation Status | Technology / Component Used | Screen / Module | Test ID | Test Description | Test Status | Test Result
REQ01 | User Registration | SRS 4.1 | YES | REGISTRATION | DONE | Supabase Auth signUp, email verification | SignUpScreen, VerifyEmailScreen | T001 | Sign up with email, password, full name; verify email confirmation flow | DONE | PASS
REQ02 | User Login (Email + Password) | SRS 4.1 | YES | LOGIN | DONE | Supabase Auth signInWithPassword | LoginScreen | T002 | Login with valid credentials; verify session created | DONE | PASS
REQ03 | Social Login (Google / Apple) | SRS 4.1 | YES | SOCIAL LOGIN | NOT STARTED | Planned: Supabase OAuth providers | LoginScreen (UI ready, backend not connected) | T003 | Login using Google/Apple OAuth flow | NOT TESTED | PENDING
REQ04 | Biometric Login (Fingerprint / Face) | SRS 4.1 | YES | LOGIN WITH BIOMETRIC | DONE | expo-local-authentication, expo-secure-store | BiometricLockScreen, LoginScreen | T004 | Enable biometric; lock app; unlock with Face ID/Fingerprint | DONE | PASS
REQ05 | Password Reset | SRS 4.1 | YES | PASSWORD RESET | DONE | Supabase Auth resetPasswordForEmail | ForgotPasswordScreen | T005 | Request password reset email; verify reset link received | DONE | PASS
REQ06 | Account Lockout on Failed Attempts | SRS 4.1 | YES | ACCOUNT SECURITY | DONE | Supabase Auth built-in rate limiting | LoginScreen (server-side enforcement) | T006 | Attempt multiple failed logins; verify lockout triggered | DONE | PASS
REQ07 | Session Management & Auto Renewal | SRS 3.4 | YES | SESSION MANAGEMENT | DONE | Supabase Auth session auto-refresh, onAuthStateChange listener | App.tsx (useAuth hook) | T007 | Verify session persists across app restarts; auto-refresh token | DONE | PASS
REQ08 | Create Expense Group | SRS 4.2 | YES | GROUP CREATION | DONE | Supabase insert to groups + group_members tables | CreateGroupScreen | T008 | Create group with name, emoji, currency, members | DONE | PASS
REQ09 | Invite Members to Group | SRS 4.2 | YES | MEMBER INVITATION | DONE | Supabase profiles search (ilike), group_members insert | CreateGroupScreen, GroupSettingsScreen | T009 | Search profiles by name/email; add to group | DONE | PASS
REQ10 | Assign Admin and Member Roles | SRS 4.2 | YES | ROLE MANAGEMENT | DONE | Supabase group_members.role column (admin/member) | GroupSettingsScreen (updateGroupMemberRole) | T010 | Toggle member role between admin and member | DONE | PASS
REQ11 | Edit Group Settings | SRS 4.2 | YES | GROUP SETTINGS | DONE | Supabase update on groups table | GroupSettingsScreen | T011 | Edit group name, emoji, currency; verify changes persist | DONE | PASS
REQ12 | Remove Members or Delete Group | SRS 4.2 | YES | MEMBER MANAGEMENT | DONE | Supabase delete from group_members; delete group with balance check | GroupSettingsScreen | T012 | Remove member; delete group; verify unsettled balance warning | DONE | PASS
REQ13 | Add Expense (Amount, Description, Payer) | SRS 4.3 | YES | ADD EXPENSE | DONE | Supabase insert to expenses + expense_splits tables | AddExpenseScreen | T013 | Add expense with amount, description, date, category, payer | DONE | PASS
REQ14 | Equal Splitting Among Participants | SRS 4.3 | YES | EQUAL SPLIT | DONE | Integer-cents arithmetic with remainder to payer | AddExpenseScreen (Equal tab) | T014 | Split equally; verify cents remainder handling | DONE | PASS
REQ15 | Unequal Splitting (Exact, Percentage, Shares) | SRS 4.3 | YES | UNEQUAL SPLIT | DONE | Integer-cents math; 3 split modes in AddExpenseScreen | AddExpenseScreen (Exact/Percent/Shares tabs) | T015 | Split by exact amount, percentage, shares; verify sum = total | DONE | PASS
REQ16 | Attach Receipt Image to Expense | SRS 4.3 | YES | RECEIPT UPLOAD | DONE | expo-image-picker for camera/gallery access | AddExpenseScreen, ScanReceiptScreen | T016 | Attach receipt photo from camera or gallery | DONE | PASS
REQ17 | Receipt Scanning with OCR (Auto Extract) | SRS 4.3 | YES | OCR SCANNING | DONE | Tesseract.js 7.0.0 on-device OCR | ScanReceiptScreen | T017 | Scan receipt; verify amount/date/vendor extracted to prefill | DONE | PASS
REQ18 | Offline Expense Entry with Auto Sync | SRS 4.3 | YES | OFFLINE MODE | NOT STARTED | Planned: AsyncStorage queue + Supabase sync | Not yet implemented | T018 | Add expense offline; verify auto-sync on reconnect | NOT TESTED | PENDING
REQ19 | Calculate Per-Member Group Balances | SRS 4.4 | YES | BALANCE CALCULATION | DONE | Real-time: SUM(splits) - SUM(settlements) via apiService | GroupDetailScreen (Balances tab) | T019 | Add expenses and settlements; verify per-member balances | DONE | PASS
REQ20 | Overall Balance Across All Groups | SRS 4.4 | YES | OVERALL BALANCE | DONE | Aggregated balance computation in HomeScreen | HomeScreen (Home tab) | T020 | Verify overall balance sums across all groups | DONE | PASS
REQ21 | Debt Simplification Algorithm | SRS 4.4 | YES | DEBT SIMPLIFICATION | DONE | Debt minimization logic in apiService | GroupDetailScreen | T021 | Verify simplified settlement suggestions | DONE | PASS
REQ22 | View Transaction History Between Members | SRS 4.4 | YES | TRANSACTION HISTORY | DONE | Supabase query filtered by member pair | MemberHistoryScreen | T022 | View expense and settlement history between two members | DONE | PASS
REQ23 | Record External Settlement | SRS 4.5 | YES | EXTERNAL SETTLEMENT | DONE | Supabase insert to settlements table | SettleUpScreen | T023 | Record settlement with amount, method, note | DONE | PASS
REQ24 | Support Partial Settlements | SRS 4.5 | YES | PARTIAL SETTLEMENT | DONE | Amount field allows any value ≤ owed balance | SettleUpScreen | T024 | Record partial payment; verify remaining balance updated | DONE | PASS
REQ25 | Update Balances on Settlement | SRS 4.5 | YES | BALANCE UPDATE | DONE | Derived balance recalculated from settlements table | GroupDetailScreen, HomeScreen | T025 | Record settlement; verify all balances updated in real-time | DONE | PASS
REQ26 | Push Notifications for New Expenses | SRS 4.6 | YES | NOTIFICATIONS | DONE | In-app notification feed (Activity tab) | HomeScreen (Activity tab) | T026 | Add expense; verify notification appears in activity feed | DONE | PASS
REQ27 | Push Notifications for Settlements | SRS 4.6 | YES | SETTLEMENT ALERTS | DONE | In-app notification feed | HomeScreen (Activity tab) | T027 | Record settlement; verify notification appears | DONE | PASS
REQ28 | Group Invitation Notifications | SRS 4.6 | YES | GROUP INVITATION | DONE | In-app notification on group_members insert | HomeScreen (Activity tab) | T028 | Add member to group; verify notification sent | DONE | PASS
REQ29 | Payment Reminder Notifications | SRS 4.6 | YES | PAYMENT REMINDERS | NOT STARTED | Planned: FCM push with scheduled triggers | Not yet implemented | T029 | Configure reminder; verify push notification received | NOT TESTED | PENDING
REQ30 | Configurable Notification Preferences | SRS 4.6 | YES | NOTIFICATION PREFS | DONE | Toggle preferences persisted to Supabase profiles | NotificationSettingsScreen | T030 | Toggle notification types; verify preferences saved | DONE | PASS
REQ31 | In-App Notification History | SRS 4.6 | YES | NOTIFICATION HISTORY | DONE | Activity tab with chronological event feed | HomeScreen (Activity tab) | T031 | View notification history with read/unread status | DONE | PASS
REQ32 | Group Default Currency Selection | SRS 4.7 | YES | CURRENCY MGMT | DONE | groups.default_currency column (ISO 4217) | CreateGroupScreen, GroupSettingsScreen | T032 | Create group with NPR/USD/EUR currency; verify stored | DONE | PASS
REQ33 | Multi-Currency Expense Conversion | SRS 4.7 | YES | MULTI-CURRENCY | DONE | Currency selection in AddExpenseScreen | AddExpenseScreen | T033 | Enter expense in different currency; verify conversion | DONE | PASS
REQ34 | Exchange Rate Caching | SRS 4.7 | YES | RATE CACHE | PARTIAL | Planned: server-side 24hr cache via Frankfurter API | Backend API (planned) | T034 | Verify cached rates used when API unavailable | NOT TESTED | PENDING
REQ35 | Spending Pattern Visual Analytics | SRS 4.8 | YES | ANALYTICS | DONE | Category breakdown, trend charts, group/member stats | AnalyticsScreen | T035 | View spending analytics dashboard with filters | DONE | PASS
REQ36 | Export Reports (PDF / CSV) | SRS 4.8 | YES | REPORT EXPORT | DONE | Export screen with format/scope selection | ExportScreen | T036 | Export report in PDF and CSV; verify data accuracy | DONE | PASS
REQ37 | Predefined and Custom Categories | SRS 4.8 | YES | CATEGORIES | DONE | Predefined categories (food, transport, etc.) with emoji icons | AddExpenseScreen | T037 | Select predefined category; verify stored with expense | DONE | PASS
REQ38 | Secure Password Storage (Hashing) | SRS 5.3 | YES | PASSWORD SECURITY | DONE | Supabase Auth bcrypt hashing (server-managed) | Supabase Auth (server-side) | T038 | Verify password never stored in plaintext | DONE | PASS
REQ39 | Encrypted Communication (HTTPS) | SRS 5.3 | YES | SECURE COMMS | DONE | Supabase enforces HTTPS/TLS for all API traffic | All network calls via @supabase/supabase-js | T039 | Verify all API calls use HTTPS | DONE | PASS
REQ40 | Access Control (Group Membership Required) | SRS 5.3 | YES | ACCESS CONTROL | DONE | requireGroupMember() / requireGroupAdmin() in apiService | apiService.ts (every group endpoint) | T040 | Attempt access without membership; verify denied | DONE | PASS
REQ41 | Input Validation (Client and Server) | SRS 5.2 | YES | INPUT VALIDATION | DONE | Client: TypeScript types + form validation; Server: Supabase constraints | AddExpenseScreen, SettleUpScreen, all forms | T041 | Submit invalid data; verify rejection with error message | DONE | PASS
REQ42 | Cross-Platform Support (iOS and Android) | SRS 2.4 | YES | CROSS-PLATFORM | DONE | React Native 0.81.5 + Expo SDK 54 (single codebase) | Entire application | T042 | Run on iOS and Android; verify identical functionality | DONE | PASS
REQ43 | Precise Decimal Money Calculations | SRS 5.5 | YES | MONEY MATH | DONE | Integer-cents arithmetic (multiply by 100, compute, divide) | AddExpenseScreen split calculations | T043 | Split odd amounts; verify no floating-point drift | DONE | PASS
REQ44 | Split Amounts Must Sum to Total | SRS 5.5 | YES | SPLIT VALIDATION | DONE | Validation in AddExpenseScreen before save | AddExpenseScreen (all 4 split methods) | T044 | Enter splits that don’t sum to total; verify rejection | DONE | PASS
REQ45 | Settlement Amount Within Owed Balance | SRS 5.5 | YES | SETTLEMENT VALIDATION | DONE | Amount capped at outstanding balance in SettleUpScreen | SettleUpScreen | T045 | Attempt settlement exceeding balance; verify capped | DONE | PASS
IMPLEMENTATION SUMMARY |  |  |  |  | 41/45 DONE | 1 PARTIAL, 3 NOT STARTED |  |  |  | 41/45 TESTED | 41/45 PASSED